## REV0.0
Item # | Severity [0-5] | Short Description | Long Description | Action Items | Status | Date Added | Date Resolved | Result
1 | 5 | Logic Level Translator VCCA/VCCB Swap | Well Crap. I knew this would be an issue so past jesse checked it… notes from 03/08/2026 " Voltage Levels? VCCA at 3V3 (pin 23, 24), VCCB at 5V (pin 1) Both correct" This is very wrong. VCCB should be 3V3 and VCCA should be 5V… as a result the translator is completely misbehaving. | 1) Flip VCCA / VCCB Rails 2) Adjust DIR accordingly 3) Face Palm | DONE | 2026-08-29 | ???
2 | 0 | Breakout UART Pins for Debug | May as well break out UART0 for programming/debugging. The defualt GP0/GP1 are used but I can also route it to GP17/GP16 so I'll do that. |  | DONE | 2026-08-29 | ???
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0 - Optional Errata Item 1 - Less optional Issue 2 - Low severity issue 3 - Medium severity issue 4 - High Severity issue 5 - Loss of function, or safety concern.

## REV1.0
Item # | Severity [0-5] | Short Description | Long Description | Action Items | Status | Date Added | Date Resolved | Result
1 | 5 | Switcher Enable OV | The enable pin on the switcher is being overvoltaged… oops. Do thinks quick, make dumb mistakes I suppose. Solution is easy enough since there's an internal PU we can just cut the trace. |  | PENDING | 2026-09-26 | n/a | Not fixing… Just cut the trace connecting U1 pin 5 to VCC.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0 - Optional Errata Item 1 - Less optional Issue 2 - Low severity issue 3 - Medium severity issue 4 - High Severity issue 5 - Loss of function, or safety concern.